## Week 1
PROJECT REPORT
Group | 2
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Share work | In Progress | Divide the project into several parts and the team leader will divide them equally among the team members
2 | Introduce | Completed | Introduce in detail the purpose and benefits of the project implementation
3 | Listed | In Progress | List functions and possible scenarios for innkeepers and customers
4 | SRS | In Progress | SRS diagram design
5 | Screen flow | In Progress | This part shows the system screens and the relationship among screens.
6 | Database | In Progress | Design database for application
7 | Code | In Progress | Implement code, start dividing next week
8 | Product backlog | In Progress | Distributing work to team members
9 | ERD | In Progress | Database design for ERD application
10 | Context diagram | In Progress | Need a redesign
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Division of work | Phạm Hưng Phát | Need to divide the work more specifically to save time
2 | Product introduction | Phạm Hưng Phát, Hoàng Minh Thuận | Words need to be changed to fit the context
3 | Working with SRS of Project Hostel Management | Phạm Hưng Phát, Nguyễn Hoàng Hải | In progress
4 | Design the necessary screens of the application | Bùi Khôi Nguyên and Trần Thiên Phúc | In progress
5 | List all the function | All members | In progress
6 | Design database | All members | In progress
7 | Implement code | All members | Need to complete the quests first
8 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | Need to finish next week
9 | Database design for ERD application | Bùi Khôi Nguyên, Trần Thiên Phúc | In progress
10 | Write down Context Diagram | Nguyễn Hoàng Hải, Phạm Hưng Phát | In progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
3 | Lack of understanding of the language makes the introduction not express the context and details of the application | In Progress | Need to refer to some more sample documents online and all members have to give their opinions
4 | Wrong database design and SRS | In Progress | Need to review the relationships of each table
5 | The design lacks some necessary screens | In Progress | Thuan will add later
6 | Code has not been implemented yet due to unresolved related issues | Pending | Complete all the tasks to start implement code
7 | Missing some components of the context diagram | In Progress
8
9
10
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database | 2022-05-27 | Database building
2 | Implement code | Pending | Add key functions to the software
3 | Testing | Pending | Test possible error cases and fix them
4 | Add necessary functions for innkeepers and users | 2022-05-27 | Update new features that users need to be able to manipulate more easily with the application
5 | Complete Context Diagram | 2022-05-27
6 | Complete SRS | 2022-05-27
7 | Comple Product Backlog | 2022-05-27
8
9
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C31: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 2
PROJECT REPORT
Group | 2
Week | <16/05/2022-22/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Listed | Completed | List functions and possible scenarios for innkeepers and customers
2 | SRS | Completed | SRS diagram design
3 | Screen flow | Completed | This part shows the system screens and the relationship among screens.
4 | Database | In Progress | Design database for application
5 | Code | Pending | Implement code, start dividing next week
6 | Product backlog | In Progress | Distributing work to team members
7 | ERD | In Progress | Database design for ERD application
8 | Context diagram | Completed | A schema is used to provide an overview of the entire system.
9 | Design layout | In Progress | Design layoutwith CSS, bootstrap, JS
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Product introduction | Phạm Hưng Phát, Hoàng Minh Thuận | Completed
2 | Working with SRS of Project Hostel Management | Phạm Hưng Phát, Nguyễn Hoàng Hải | Completed
3 | Design the necessary screens of the application | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
4 | List all the function | All members | Completed
5 | Design database | All members | In Progress
6 | Implement code | All members | Pending
7 | Write Product Backlog | Hoàng Minh Thuận, Phạm Hưng Phát | In Progress
8 | Database design for ERD application | Bùi Khôi Nguyên, Trần Thiên Phúc | Completed
9 | Write down Context Diagram | Nguyễn Hoàng Hải, Phạm Hưng Phát | Completed
10 | Layout | Bùi Khôi Nguyên, Trần Thiên Phúc | In Progress
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Members meeting on time, resulting in delayed project progress | In Progress | The team leader needs to make stricter rules for the members to follow
2 | No clear division of work | In Progress | The team leader needs to learn about the tasks to distribute them more evenly
4 | Wrong database design and SRS | Pending | Need to review the relationships of each table
5 | The design lacks some necessary screens | Completed | Solved
6 | Code has not been implemented yet due to unresolved related issues | In Progress | Complete all the tasks to start implement code
7 | Missing some components of the context diagram | Completed | Group discussion to find a solution
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database | 27/05/2022 | Database building
2 | Implement code | Pending | Add key functions to the software
3 | Testing | Pending | Test possible error cases and fix them
4 | Completing the product backlog | 27/05/2022 | Let everyone follow and do their own thing
5 | Completing the layout | 27/05/2022 | Tran Thien Phuc and Bui Khoi Nguyen
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C31: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue